## Sheet4
Initiative Name | Initiative Owner | Supported By | AI Champions | AI Champions Network
Gen AI Champions Initiative@SWD |  |  | Acharyulu K Karthik (BD/SWD-FSB5) | Singh Nilesh Kumar (BD/SWD-BEA6)
| Benno Oommen | Shanti Prasad | Murugaboopathi Pillaiyar (BD/SWD-FSB6) | Somdev Rajauria (BD/SWD-BEA7)
|  |  | Manish Kumar (BD/SWD-DOE2) | Madhanreyan V (BD/SWD-BEA9)
|  |  | Nagaraj Pandian (BD/SWD-BEA9) | Myilsamy Lakshmanan (BD/SWD-FSB3)
|  |  | Ganeshamurthi Ramasamy (BD/SWD-FSB6) | Veereshkumar Gandhaveedi (BD/SWD-FSB4)
|  |  | Sridhar Munivenkataram (BD/SWD-TMA6) | Sivasankar Angamuthu (BD/SWD-FSB5)
Topic | Sub topics | Progress | Lead | Key Points | Completion Date
AI Champions @SWD |  | 38.75%
| AI Tech Talk | 50% | Acharyulu K Karthik (BD/SWD-FSB5) | 2 tech Talks done | 2026-12-31
| ACO - AI Credit Optimizer | 50% | Acharyulu K Karthik (BD/SWD-FSB5) | Idea shared with BD global | 2026-10-31
| BD India Accord Gen AI CoC | 50% | Benno
| AI Trainings |  | Nagaraj Pandian (BD/SWD-BEA9) | Langchain, LangGraph
| Claude POC |  | Somdev Rajauria (BD/SWD-BEA7)
| Sandbox for SWD | 100% | Murugaboopathi Pillaiyar (BD/SWD-FSB6) | Its Available | 2026-07-30
| Easy Info Access - All @one place - Dashboard | 50% | Boopathi/Nilesh |  | 2026-08-31
| Repository - Capture the information - AI topics Gen AI Stories |  | Shanthi
| Ideas Usecase - Chatbot |  | Veeresh - Nilesh
| Calendar for all AI Meets |  | Benno
| Hackathon | 0%
| Gen AI Stories | 10%
| Gen AI News Letter @SWD | 0%
Define metrics to measure AI benefits (effort savings, productivity).
Create a central tracking mechanism (Excel → dashboard/Power BI/JIRA) for all AI activities.
Weekly internal syncs and monthly global connects established.

## Activity_Sessions
Sub Topic | Session Title | Date | Status | Owner | Link
AI Tech Talk | Building AI-Powered Applications with Spring MCP | 2026-06-10 | Completed | Sivasankar & Sivasubramanian | https://inside-docupedia.bosch.com/confluence/display/IGPMMCR/System+architecture
AI Tech Talk | DevDock - AI Sandbox for Bosch Developers | 2026-07-03 | Completed | Murugaboopathi
AI Tech Talk | A2A Protocol in Action: Agent Communication and Workflow Orchestration |  | Upcoming | Srilakshmy Sooraj
ACO - AI Credit Optimizer | Pilot Testing V1 |  | Completed | Acharyulu K Karthik | https://inside-docupedia.bosch.com/confluence/display/IGPMMCR/System+architecture
ACO - AI Credit Optimizer | V2 Testing |  | Upcoming | Acharyulu K Karthik